## Slide 1: Developing an Intergenerational Supported Housing Project
For young parents, children and older adults
Gill Taylor – Strategic Lead for Vulnerable Adults & Single Homelessness
& Yasmin Drakes – Commissioning Officer, Young People’s Services

## Slide 2: Background
In 2016, Haringey Council conducted a strategic review of its supported housing services
It concluded with a needs analysis and suite of recommendations, which were approved by Cabinet in 2017
The review recommended that Haringey should work towards the principles of:
  Community Inclusion
  Commissioning for the future
The review recommended the ‘exploration of the reconfiguration of a sheltered scheme into supported housing for young parents as an intergenerational service’

## Slide 3: Context – Older Adults
In Haringey we identified that:
Older people stated they felt isolated and lonely in these schemes and required more social and wellbeing based support
Older people felt there were not enough opportunities to utilise their skills and wealth of knowledge within the scheme
Older people’s needs and wishes had changed over time, therefore sheltered housing across the borough was in lower demand
Communal spaces in sheltered housing schemes were frequently under-utilised

## Slide 4: Context – Young Parents
Some young parents require a period of support after having their child, to allow them to develop their independent living skills
The borough has no dedicated supported housing service for young parents. They are either accommodated in TA or mother and baby units out of the area
A growing proportion of young parents have been identified as homeless (3.6%).
Research has highlighted that 49% of young parents aged between 18 and 25 feel isolated or often or always lonely
Haringey’s Care Leaver young parents may not have older positive role models from which to learn from
Notes: https://www.redcross.org.uk/about-us/news-and-media/media-centre/press-releases/press-release-shocking-extent-of-loneliness-faced-by-young-mothers-revealed##

## Slide 5: Intergenerational scheme aims
#1: Improving the health and wellbeing outcomes of all three cohorts
#2: Sharing and developing skills
#3: Encouraging community inclusion and integration
#4: Testing an innovative solution to an identified housing need

## Slide 6
Scheme development process
1. Identify appropriate site
2. Consult with residents in the sheltered housing scheme
3. Consult with young parents and organisations representing young parents
4. Form a steering group of older residents and representatives of young parents to determine the operational aspects of the project
5. Develop a support provider partnership to support both older and younger residents and facilitate intergenerational activities
6. Commission an independent evaluation of the scheme
7. Make practical changes to the scheme to preparation for young parents’ move-in
8. Young Parent’s move in & intergenerational activities commence

## Slide 7: Challenges and solutions
Challenges faced | Solutions
Resident resistance to the project | Thorough consultations & 1:1’s with residents Seek an alternative scheme if there is no appetite
Resident concerns about the practicalities of intergenerational living | Be clear about the benefits, the possible issues and the mitigations you will put in place to counter such issues Set up a resident’s/ young parent’s steering group to allow both cohorts to set house rules, decide how the scheme will run on a day-to-day basis
Financing aspects of the scheme | Work with local VCS organisations Apply to grants and charities for any goods needed to make the scheme YP friendly

## Slide 8
Young parents’ will start moving into the scheme in April
Steering group residents are working to develop a ‘warm welcome’ for the young parents when they move-in
Building a TAC model (Team Around the Community) – making links with local children’s centres and health visitors and other young parents support services to ensure young parents receive as much support as possible
Seeking an independent evaluation partner
Preparing the flats and scheme to ensure it is young parent and baby friendly
Steering group residents are drafting the ‘house rules’ which will be the same for all residents regardless of age
Where are we now?

## Slide 9: Lessons learnt (so far!)
Political support for the scheme is essential
Undertake thorough resident consultations
Recognise that not all environments would be suitable for this type of scheme
Be patient! Implementation may be slow
Let the older people and younger people co-produce the project and determine how the scheme will work
Invest in support staff to bring the generations together and facilitate joint activities
Seek professional health and safety guidance
Start slowly and build upwards

## Slide 10: Any Questions?